## Sheet1
WORKPLAN: LA ELEMENTARY STARTUP |  |  | Lead | Support | 2005-05-30 | 2005-06-06 | 2005-06-13 | 2005-06-20 | 2005-06-27 | 2005-07-04 | 2005-07-11 | 2005-07-18 | 2005-07-25 | 2005-08-01 | 2005-08-08 | 2005-08-15 | 2005-08-22 | 2005-08-29 | 2005-09-05
Student Enrollment & Registration
| Set enrollment deadlines and objectives |  | Principal | Principal | bar: 2005-05-30
| Refine and print collateral materials for LA families |  | COO | bar: 2005-05-30
| Recruit students |  |  |  | 2005-06-06: ¦------------------------------------------->
|  | Present at churches, child care centers, etc | Principal | Principal | 2005-06-13: ¦--------------->
|  | Hand out flyers at supermarket | Principal | Principal | bar: 2005-06-06 to 2005-06-20
|  | Canvass neighborhood | Principal | Principal | bar: 2005-06-06 to 2005-06-20
|  | Conduct info sessions | Principal | Principal | 2005-06-13: x x; 2005-06-20: x x
|  | Identify other advertising vehicles if needed | Principal | Principal | 2005-06-20: ¦------->
| Conduct Lottery |  | Principal | Cathy | bar: 2005-06-27
| Register students |  | OM | Cathy | 2005-07-11: ¦--------------->
| Input all student info into PowerSchool |  | OM | Cathy | 2005-07-25: ¦--------------->
HR
Hire Office Manager
|  | Advertise openings | Recruiter |  | 2005-05-30: ¦------------------->
|  | Screen and interview candiates | Principal | Principal | 2005-06-06: ¦------------------->
|  | Check for technical ability if needed | Cathy |  | 2005-06-13: ¦------------------->
|  | Conduct reference checks | Principal | Recruiter | 2005-06-20: ¦------------------->
Hire educators
|  | Select and train site hiring committee | Principal | COO | 2005-06-06: ¦------------------->
|  | Advertise openings | Recruiter |  | 2005-05-30: ¦-------------------------------------------------->
|  | Screen, interview and demo candiates | Principal | Principal | 2005-06-06: ¦---------------------------------------------------------->
|  | Conduct reference checks | Principal | Principal | 2005-06-13: ¦---------------------------------------------------------->
| Set compensation |  | Principal | CFO
| Send offer letters |  | Recruiter
| Conduct orientation |  | Principal | COO
Program
| Conduct summer training |  | CAO |  | 2005-08-01: ¦------------------------------------->
| Identify key areas for coaching |  | CAO |  | 2005-08-08: ¦---------------------------------------->
Finance
| Develop 2005-2006 budget |  | Financial Analyst |  | 2005-05-30: ¦------------------------>
| Review finance/accounting policies and practices |  | Financial Analyst | bar: 2005-05-30
| Meet with District/COE RE funds flow |  | A/R Grants Accountant | bar: 2005-06-27
Procurement
| Secure FFE |  | Director, Real Estate |  | 2005-05-30: ¦---------------------------------------------------------------------------------------------------->
| Order curriculum materials |  | Pricipal | CAO | 2005-06-13: ¦-------------->
| Establish contracts with vendors as needed |  | Pricipal | CFO | 2005-06-06: ¦---------------------------------------------------------------------------------------------------->
Facilities
| Ensure builidng is renovated |  | Developer | Director of Real Estate | 2005-05-30: ¦-------------------------------------------------------------------------------------------------------------------------------------------->
| Negotiate/coordinate daily operations with church |  | Principal | Director of Real Estate | 2005-06-20: ¦--------------->
Goverance
| Establish Site Advisory Counsel |  | Principal | Principal | 2005-08-08: ¦--------------->
| Complete MOU with LAUSD |  | Tom |  | 2005-06-20: ¦--------------->